## Plan
Plan ID | Plan name | Date of export
5NJSIaJ3aUy71Src4WDHC8kAGwkW | R26-IT-050 | 2026-10-14

## Consolidated Data
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date (proposed) | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
2uhUxZ8lNU-76gScd8hYCskAGn9G | Prepare POI Dataset and Define Itinerary Constraints | planing |  | Not started | Medium | DENIYAWATTA D N it22895196 | WIJESINGHE I.D.W. it22555458 | 2026-08-20T00:00:00.000Z | 2026-09-05 |  |  | true | [5 empty] | Proposed planning date; original Planner Created Date: 2026-10-14.
7f-IuTu1FUGYSqGf0kDPLskAGs_X | Develop and Test Intelligent Tour Package Generation | Executing |  | Not started | Medium | DENIYAWATTA D N it22895196 | WIJESINGHE I.D.W. it22555458 | 2026-09-06T00:00:00.000Z | 2026-10-05 |  |  | true | [5 empty] | Proposed planning date; original Planner Created Date: 2026-10-14.
g2YqiZ4ZIEOi9x7sD82q3MkAKrBP | Prepare POI Dataset and Define Itinerary Constraints | planing |  | Not started | Medium | KUMARASINGHE K.G.A.M.S.D.C it22224866 | WIJESINGHE I.D.W. it22555458 | 2026-08-20T00:00:00.000Z | 2026-09-05 |  |  | true | [5 empty] | Proposed planning date; original Planner Created Date: 2026-10-14.
C_1ZouY4sUOs8SCSLhKN5MkAHqdG | Develop and Evaluate Personalized Itinerary Optimization | Executing |  | Not started | Medium | KUMARASINGHE K.G.A.M.S.D.C it22224866 | WIJESINGHE I.D.W. it22555458 | 2026-09-06T00:00:00.000Z | 2026-10-05 |  |  | true | [5 empty] | Proposed planning date; original Planner Created Date: 2026-10-14.
NbMysNGaqUS62GvjKM_ogskADNJ_ | Prepare Road-Risk and Vehicle Datasets | planing |  | Not started | Medium | WIJESINGHE I.D.W. it22555458 | WIJESINGHE I.D.W. it22555458 | 2026-08-20T00:00:00.000Z | 2026-09-05 |  |  | true | [5 empty] | Proposed planning date; original Planner Created Date: 2026-10-14.
2zn5PrmqvUOt4VN-dBXeJskAPL7W | Develop and Test Route-Risk Analysis and Vehicle Recommendation | Executing |  | Not started | Medium | WIJESINGHE I.D.W. it22555458 | WIJESINGHE I.D.W. it22555458 | 2026-09-06T00:00:00.000Z | 2026-10-05 |  |  | true | [5 empty] | Proposed planning date; original Planner Created Date: 2026-10-14.
VsRozsKmZkuUG-J6seG998kADhYM | Prepare Landmark Image Dataset and Train Recognition Model | planing |  | Not started | Medium | MADUSHAN M it22214720 | WIJESINGHE I.D.W. it22555458 | 2026-08-15T00:00:00.000Z | 2026-09-05 |  |  | true | [5 empty] | Proposed planning date; original Planner Created Date: 2026-10-14.
BQ_UJodl7kqhYeZY3cmLOckALICu | Integrate and Evaluate Landmark Recognition and AI Tourist Guide | Monitoring and controlling |  | Not started | Medium | MADUSHAN M it22214720 | WIJESINGHE I.D.W. it22555458 | 2026-09-06T00:00:00.000Z | 2026-10-10 |  |  | true | [5 empty] | Proposed planning date; original Planner Created Date: 2026-10-14.

## Tasks
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date (proposed) | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
2uhUxZ8lNU-76gScd8hYCskAGn9G | Prepare POI Dataset and Define Itinerary Constraints | k856GZoETEK7buI_Vki-b8kAEUxQ |  | Not started | Medium | 4163241f-b455-45dc-81e9-3efc81435c0c | 2b2cda3b-30bc-47ae-b945-d53decd14fa8 | 2026-08-20T00:00:00.000Z | 2026-09-05 |  |  | true | [5 empty] | Proposed planning date; original Planner Created Date: 2026-10-14.
7f-IuTu1FUGYSqGf0kDPLskAGs_X | Develop and Test Intelligent Tour Package Generation | huoNleuiFUmvVw2Qd9gPSMkAF5GO |  | Not started | Medium | 4163241f-b455-45dc-81e9-3efc81435c0c | 2b2cda3b-30bc-47ae-b945-d53decd14fa8 | 2026-09-06T00:00:00.000Z | 2026-10-05 |  |  | true | [5 empty] | Proposed planning date; original Planner Created Date: 2026-10-14.
g2YqiZ4ZIEOi9x7sD82q3MkAKrBP | Prepare POI Dataset and Define Itinerary Constraints | k856GZoETEK7buI_Vki-b8kAEUxQ |  | Not started | Medium | 9f2d8e1d-77f3-47d4-9970-afe8e4c39b23 | 2b2cda3b-30bc-47ae-b945-d53decd14fa8 | 2026-08-20T00:00:00.000Z | 2026-09-05 |  |  | true | [5 empty] | Proposed planning date; original Planner Created Date: 2026-10-14.
C_1ZouY4sUOs8SCSLhKN5MkAHqdG | Develop and Evaluate Personalized Itinerary Optimization | huoNleuiFUmvVw2Qd9gPSMkAF5GO |  | Not started | Medium | 9f2d8e1d-77f3-47d4-9970-afe8e4c39b23 | 2b2cda3b-30bc-47ae-b945-d53decd14fa8 | 2026-09-06T00:00:00.000Z | 2026-10-05 |  |  | true | [5 empty] | Proposed planning date; original Planner Created Date: 2026-10-14.
NbMysNGaqUS62GvjKM_ogskADNJ_ | Prepare Road-Risk and Vehicle Datasets | k856GZoETEK7buI_Vki-b8kAEUxQ |  | Not started | Medium | 2b2cda3b-30bc-47ae-b945-d53decd14fa8 | 2b2cda3b-30bc-47ae-b945-d53decd14fa8 | 2026-08-20T00:00:00.000Z | 2026-09-05 |  |  | true | [5 empty] | Proposed planning date; original Planner Created Date: 2026-10-14.
2zn5PrmqvUOt4VN-dBXeJskAPL7W | Develop and Test Route-Risk Analysis and Vehicle Recommendation | huoNleuiFUmvVw2Qd9gPSMkAF5GO |  | Not started | Medium | 2b2cda3b-30bc-47ae-b945-d53decd14fa8 | 2b2cda3b-30bc-47ae-b945-d53decd14fa8 | 2026-09-06T00:00:00.000Z | 2026-10-05 |  |  | true | [5 empty] | Proposed planning date; original Planner Created Date: 2026-10-14.
VsRozsKmZkuUG-J6seG998kADhYM | Prepare Landmark Image Dataset and Train Recognition Model | k856GZoETEK7buI_Vki-b8kAEUxQ |  | Not started | Medium | 05a5869d-58a6-4581-a55a-0625d12077e5 | 2b2cda3b-30bc-47ae-b945-d53decd14fa8 | 2026-08-15T00:00:00.000Z | 2026-09-05 |  |  | true | [5 empty] | Proposed planning date; original Planner Created Date: 2026-10-14.
BQ_UJodl7kqhYeZY3cmLOckALICu | Integrate and Evaluate Landmark Recognition and AI Tourist Guide | X0sgixBW1UKphWl3IGJ5CckAAcrB |  | Not started | Medium | 05a5869d-58a6-4581-a55a-0625d12077e5 | 2b2cda3b-30bc-47ae-b945-d53decd14fa8 | 2026-09-06T00:00:00.000Z | 2026-10-10 |  |  | true | [5 empty] | Proposed planning date; original Planner Created Date: 2026-10-14.

## Goals
Goal ID | Goal name | Status | Priority | Start date | Finish date | Connected tasks | Notes

## Buckets
Bucket ID | Bucket Name
4hbUG_fv6kmejG-FxTv0FckAKMDr | To do
k856GZoETEK7buI_Vki-b8kAEUxQ | planing
huoNleuiFUmvVw2Qd9gPSMkAF5GO | Executing
X0sgixBW1UKphWl3IGJ5CckAAcrB | Monitoring and controlling
Ni388HgElEG1pEO-rcIKl8kACDj0 | Closing

## Users
User ID | User Name | Email
4163241f-b455-45dc-81e9-3efc81435c0c | DENIYAWATTA D N it22895196 | it22895196@my.sliit.lk
2b2cda3b-30bc-47ae-b945-d53decd14fa8 | WIJESINGHE I.D.W. it22555458 | it22555458@my.sliit.lk
9f2d8e1d-77f3-47d4-9970-afe8e4c39b23 | KUMARASINGHE K.G.A.M.S.D.C it22224866 | it22224866@my.sliit.lk
05a5869d-58a6-4581-a55a-0625d12077e5 | MADUSHAN M it22214720 | it22214720@my.sliit.lk